## Data Alignment Support
S.No | Actions / Tasks | Task # | Target date | Start date | End Date | Status
1 | Substation - Find_in EO | 596310 | 2023-06-26 | 2023-06-23 | 2023-06-26 | Completed
2 | Substation -No Location ID - Maximo | 596461 | 2023-06-27 | 2023-06-26 | 2023-06-29 | Completed
3 | Circuit Breaker (Composite Switch) - South | 663320 | 2023-07-03 | 2023-07-03 | 2023-07-03 | Completed
4 | Primary with more than 1 voltage | 620974 | 2023-07-07 | 2023-07-03 | 2023-07-07 | Completed
5 | Pole Structure VS Pole Status Conflict - 239 items | 705316 | 2023-07-10 | 2023-07-07 | 2023-07-10 | Completed
6 | Ring Main Unit (FS) - Find in EO | 596258 | 2023-07-12 | 2023-07-10 | 2023-07-13 | Completed
7 | Circuit Breaker - Fix_EO_No_Asset_ID - 2221 items | 596285 | 2023-07-18 | 2023-07-14 | 2023-07-18 | Completed
8 | Circuit Breaker - Find in EO | 596286 | 2023-07-19 | 2023-07-19 | 2023-07-21 | Completed
9 | Substations - ADG, Locality and Class | 638498 | 2023-07-26 | 2023-07-25 |  | Hold
10 | Isolator_Disconnectors_Find in MX | 596491 | 2023-08-15 | 2023-08-04 | 2023-08-15 | Completed
11 | Earth Switch_Find Maximo Asset ID | 596487 | 2023-08-09 | 2023-08-04 | 2023-08-09 | Completed
12 | Substations - MX data exists, EO data unknown, unlinked or doesnt exist | 731175 | 2023-08-16 | 2023-08-07 | 2023-08-16 | Completed
13 | Task# 734686 - Pole Structures missing EP Poles | 734686 | 2023-08-22 | 2023-08-22 | 2023-08-22 | Completed
14 | Task# 734694 - Poles with blank configuration | 734964 | 2023-08-24 | 2023-08-16 |  | In Progress
15 | Task# 734697 - Poles with no Pole Structure above them | 734967 | 2023-08-24 | 2023-08-16 |  | In Progress
16 | Task# 734720 - Pole and Pole Structures with no location geometry | 734720 | 2023-08-24 | 2023-08-16 |  | In Progress
17 | Task# 734728 - 132kv Poles that belong to TRANSMISSION | 734728 | 2023-08-24 | 2023-08-16 |  | In Progress
18 | Task# 736967 - Pole Usage attribute needs empty-ing and removing | 736967 | 2023-08-24 | 2023-08-16 |  | In Progress

## Data Alignment Cleansing
S.No | Task # | Asset Type | Task | Received date | Input received | Prod Completed | Pending | QC Completed | Comp % | Status
1 | 600944 | Ring Main Unit (FS ) | RMU FS Fix EO duplicated use of Asset Id | 2023-03-09 | 323 | 323 | 0 | 323 | 100% | Completed
2 | 631015 | Windfarm | Windfarm Identification | 2023-04-17 | 261 | 261 | 0 | 261 | 100% | Completed
3 | 638948 | Metal clad switch | MCSwitch 1331 | 2023-05-16 | 1056 | 1056 | 0 | 1056 | 100% | Completed
4 | 658321 | Substation | Substation With Poor NRN | 2023-05-16 | 708 | 708 | 0 | 708 | 100% | Completed
5 | 621719 | Transformer | Multi Transformer Substations | 2023-05-29 | 888 | 888 | 0 | 888 | 100% | Completed
6 | 0 | NRN | All Voltages No NRN 2023-05-30 | 2023-06-01 | 419 | 419 | 0 | 419 | 100% | Completed
7 | 596490 | Switch Disconnectors | Switch Disconnectors - 118 items | 2023-06-13 | 117 | 117 | 0 | 117 | 100% | Completed
8 | 658321 | NRN | LV NRN non 12 Digit | 2023-06-22 | 15050 | 15050 | 0 | 15050 | 100% | Completed
9 | 688759 | Windfarm | Windfarm Cleansing | 2023-06-22 | 13 | 13 | 0 | 13 | 100% | Completed
10 | 596310 | Substation | Substation - Find_in_EO | 2023-06-28 | 925 | 925 | 0 | 925 | 100% | Completed
11 | 596461 | Substation | Substation - Find_in_Maximo | 2023-07-05 | 1213 | 1213 | 0 | 1213 | 100% | Completed
12 | 663320 | Circuit Breaker | CB-Composite Switch | 2023-07-06 | 2927 | 2927 | 0 | 2927 | 100% | Completed
13 | 705316 | Pole | Pole Structure VS Pole Status Conflict - 239 items | 2023-07-13 | 239 | 239 | 0 | 239 | 100% | Completed
14 | 596258 | Ring Main Unit (FS ) | Ring Main FS - Find_in_EO | 2023-07-20 | 620 | 620 | 0 | 620 | 100% | Completed
15 | 596285 | Circuit Breaker | Circuit Breaker - Fix_EO_No_Asset_ID - 2221 items | 2023-07-21 | 2221 | 2221 | 0 | 2221 | 100% | Completed
16 | 596286 | Circuit Breaker | Circuit Breaker - Find in EO - 901 Items | 2023-07-25 | 901 | 901 | 0 | 901 | 100% | Completed
17 | 663320 | Circuit Breaker | CB - Composite Switch - Eclipse Model- Part2 | 2023-08-08 | 243 | 243 | 0 | 200 | 82% | InProgress
18 | 596487 | Earth Switch | Earth Switch_Find Maximo Asset ID | 2023-08-09 | 6120 | 3454 | 2666 | 1488 | 24% | InProgress
19 | 620974 | Primary Subsatation | Primary with more than 1 voltage | 2023-08-16 | 107 | 97 | 10 | 40 | 37% | InProgress

## Users
Users | Task
Santhosh Pilla | Data Alignment Support
Ravi Pasumarty | Data Alignment Support
Venkatesh Javvaji | Data Alignment Cleansing
Suchitra Beura | Data Alignment Cleansing
Sahiti Kanta | Data Alignment Cleansing
Subramanyam Asupu | Data Alignment Cleansing
Sivanithya Dhaladhuli | Data Alignment Cleansing
SaiKiran Dasari | Data Alignment Cleansing
Saikiran Gampala | Data Alignment Cleansing
Betala Vinay | Data Alignment Cleansing
Nagaraju Akoju | Data Alignment Cleansing
Sindhu Kusuma | Data Alignment Cleansing